## Slide 2
Making the Most of Project Professional When Managing Multiple Projects (PC336)
Cindy Lewis, PMP, PMI-SP, MCITP, MCTS, MCT
Senior Project Advisor
Advisicon, Inc.
Concepts presented may be applied to Project Std/Pro 2003, 2007 and 2010
@LewisCindy #PC336 #mspc12

## Slide 3: Meet Cindy
Scheduling with Microsoft Project for nearly 20 years
Project Professional Certification SME 2003, 2007, 2010
Co-author MVP Press, Advisicon Publishing, Dynamic Scheduling
Western Michigan PMI Director of Public Relations
PMI TheProject2012 collegiate competition committee
Cindy Lewis, PMP, PMI-SP, MCITP, MCTS, MCT
Senior Project Advisor
Advisicon, Inc.
@LewisCindy #PC336 #mspc12

## Slide 4: Session Objectives
In this session, participants will learn the benefits of using Project Professional to manage multiple projects and drive project selection decisions.
Some critical topics of focus include:
  Experiencing a customer evolve their business through this solution
  Harnessing workloads with a limited set of shared resources
  Creating an integrated master schedule with cross-project links
  Balancing staffing and project selection decisions across a company
@LewisCindy #PC336 #mspc12

## Slide 5
Goodyear Skate Park Arizona
Charles Goodyear
Dec 1800 – July 1860
Danville, VA

## Slide 6
Customer Profile

## Slide 7
Problem – Job Management
Tom Keane and Ron Bartalucci
J.L. Becker Company
customer
@LewisCindy #PC336 #mspc12

## Slide 8: J.L. Becker Company
General Info
Minuses
Created in 1970
Plymouth, Michigan
Commercial Heating Equipment
Putting out fires
Unrealistic promises
Department isolation
Business decisions impossible to make
Pluses
Top reputation
Quality backed by owner
No shortage of work
Experienced workforce/long-term employees
@LewisCindy #PC336 #mspc12

## Slide 9
50
©J.L. Becker Company

## Slide 10
Demonstrations

## Slide 11
J.L. Becker Project Schedules
Independent Projects
demo
@LewisCindy #PC336 #mspc12

## Slide 12
1
Shared Resource Pool
2
Master Projects, Critical Path
3
Cross-Project Links
4
Shared Resource Assignments, Identifying Issues
5
Resolving Overallocated Resources, Leveling
Solution/Implementation Demos
@LewisCindy #PC336 #mspc12

## Slide 13
1
Shared Resource Pool
2
3
4
5
Solution/Implementation Demos
@LewisCindy #PC336 #mspc12

## Slide 14
Resource Pool
Creation and linking to projects
demo
@LewisCindy #PC336 #mspc12

## Slide 15
1
2
Master Projects, Critical Path
3
4
5
Solution/Implementation Demos
@LewisCindy #PC336 #mspc12

## Slide 16
Master Projects
Master/sub projects and consolidated projects
demo
@LewisCindy #PC336 #mspc12

## Slide 17
Critical Path
Project versus program level Critical Path
demo
@LewisCindy #PC336 #mspc12

## Slide 18
1
2
3
Cross-Project Links
4
5
Solution/Implementation Demos
@LewisCindy #PC336 #mspc12

## Slide 19
Cross-Project Links
Dependencies across projects
demo
@LewisCindy #PC336 #mspc12

## Slide 20
1
2
3
4
Shared Resource Assignments, Identifying Issues
5
Solution/Implementation Demos
@LewisCindy #PC336 #mspc12

## Slide 21
Resource Assignments
Viewing assignments across linked projects
demo
@LewisCindy #PC336 #mspc12

## Slide 22
Overallocated Resources
Identifying overallocations
demo
@LewisCindy #PC336 #mspc12

## Slide 23
1
2
3
4
5
Resolving Overallocated Resources, Leveling
Solution/Implementation Demos
@LewisCindy #PC336 #mspc12

## Slide 24
Resolving Overallocations
Resource modifications by resource pool manager
demo
@LewisCindy #PC336 #mspc12

## Slide 25
Leveling Resources
Using leveling to solve overallocations
demo
@LewisCindy #PC336 #mspc12

## Slide 26
1
Shared Resource Pool
2
Master Projects, Critical Path
3
Cross-Project Links
4
Shared Resource Assignments, Identifying Issues
5
Resolving Overallocated Resources, Leveling
Recap of Demonstrations
@LewisCindy #PC336 #mspc12

## Slide 27
Lessons Learned

## Slide 28: Resource Pool Tips
Unlink
Relink
Project Summary Row On
Resource Pool DO NOT DELETE
One Pool Manager
Centralize Pool
and Files
Quick consolidation where possible
Best suited for small enterprise

## Slide 29
Takeaways

## Slide 30: Suggesting Software Based on PM Maturity
@LewisCindy #PC336 #mspc12

## Slide 31
Obtaining the Free PPM Scalability Lifecycle
In both English and Spanish
Available in Visio
Also within the PDF on Choosing Project Server
http://tinyurl.com/73av76z
@LewisCindy #PC336 #mspc12

## Slide 32: Next Steps
Resources
MSPC12 Sessions
www.advisiconblog.com
Presentation resources
Preview of sessions
Other Sessions from Advisicon:
PC 212 Landing Strategy in 3 Steps (Javier Gonzalez and Rene Alvarez of Advisicon Mexico)
PC 315 - Journey from 2007-2010 (Customer Sol’n - Meijer)
PC 322 – Integrating Data from External LOB Systems (SAP, ClickSoft, etc.) for Strategic Resource Planning & Forecasting (Tim Runcie, MVP and Chetan Patel)
@LewisCindy #PC336 #mspc12

## Slide 33
Thank You for Attending

## Slide 34: Connect with Cindy
  cindy.lewis@advisicon.com
  www.linkedin.com/in/cindylewis2
  @LewisCindy
@LewisCindy #PC336 #mspc12

## Slide 35
© 2012 Microsoft Corporation. All rights reserved. Microsoft, Windows, Windows Vista and other product names are or may be registered trademarks and/or trademarks in the U.S. and/or other countries.
The information herein is for informational purposes only and represents the current view of Microsoft Corporation as of the date of this presentation. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information provided after the date of this presentation. MICROSOFT MAKES NO WARRANTIES, EXPRESS, IMPLIED OR STATUTORY, AS TO THE INFORMATION IN THIS PRESENTATION.